OASIS Sensory Partners Work Plan #4

Revision Date: June 17th, 2014

Approved: September 24th, 2014								Updated: April 28, 2015

| Item | Action | Lead | Status | Completion Date |
| --- | --- | --- | --- | --- |
| Social Media | Using the OASIS Twitter account do two “tweets per this year. #1- Prewrite – Tweets #2 Tweet: “accessibility is everyone’s responsibility” with the AODA link Post tweets on agencies sites including Facebook if agencies have Facebook | OASIS Rep:Jane Andrea All | Andrea to follow up with Jane as to who the OASIS webmaster is to post our tweet | September 23, 2014 Tweet One May 1, 2015 May 8, 2015 |
| DSO Website List of agencies Request to be listed | Develop a letter as follow up to our recent training including evaluation quotes within the letter formally requesting linkages tor OASIS SP agencies on DSO website Website: SP on DSO website New Letter or conversations with the DSO EDs regarding our proposal “Sensory Loss Intake Information”? | Andrea Andrea Roxanna and Karen C. | Andrea will draft a letter to share via email for approval by end of October 2014 | November 2014 May 1, 2015 June 19, 2015 |
| OASIS Sensory Partner’s Board Chair conference call | As needed, connection with Board chairs on strategic level vs operational level | Roxanna |  | Review annually |
| DS Provincial Network | OASIS Rep DS Provincial Network Rep As Standing Agenda item: OASIS Board minutes and Provincial Network minutes | Andrea Andrea Andrea | Jane Joris (confirmed June 23, 2014) Created the concept of standing agenda item “HOT POINTS’ for Chair to bring forward to OASIS rep | September 23, 2014 Add on to Agenda All Partners |
| DSO Strategy | Ensure DSO Strategy is on the Provincial Network Table | Karen C. | COMPLETED AS of December 10, 2014 DS Employment and Modernization Fund Submission If Fund Submission (above) not accepted then send a letter to the DSO EDs. | September 23, 2014 October 24, 2014 Lead agency DBOS |
| Update Information Package | To include new member RCH | Roxanna | What a can of worms Refer to minutes of September 24, 2014 for next steps | January 20, 2015 |
| Categorization of organizations | Research search engines (which agencies come up when DS, Deaf, DeafBlind are searched) Easily accessible to consumer? | Des Des |  | April 28th, 2015 |
| Research Parent Groups in Ontario | How many groups in Ontario? (Refer to Jan. 20th, 2015 minutes for the names of some parent groups) How active are they? Should contact be made in terms of our work? Presentations Marketing packages | Karen B. |  | June 19th, 2015 |
| School Packages | Development of parent package that could go through school to parent Milton, London, Belleville, Brantford | Chris |  | June 19th, 2015 |
| Membership | Add to TOR a Participation standard 50-75% up for further discussion |  |  | April 28, 2015 |
| CHS | - Membership - not an OASIS member - Any DS spin? |  | Further discussion on linkages with CHS that could warrant an invite to future meeting | June 19th, 2015 |
| DS Agencies -deaf -deaf blind -blind | Development of a strategy to do further linkages with DS agencies who support individuals with sensory needs | Roxanna | include Stewart Homes and other private providers, OPRs | April 28, 2015 |
| FOCUS | Community of Practice – presentation Domains | Roxanna | Apply to focus for a presentation at the Community of Practice Further review the development of domain related to sensory issues | OASIS Conference May 2015 |
| Specialized Network of Care (4) | Videoconference presentation |  | Develop a video conference presentation | June 19th, 2015 |
| First Nations | - research - grant - deaf, hard of hearing, deafblind, blind, visually impaired |  | Development of a research project/grant focusing on First Nations and related sensory needs of sector | 2016 |
| Fee for Service | Develop information about a FFS structure, re: work done by CNIB for intervenor services, including Ministry interpretation on the Eldridge case | Cindy | Outstanding | Fall 2015 |
| MCSS – Karen Chan | Follow up via email with Karen Chan, ADM on paper, presentations re DSOs | Roxanna | Overview provided of contact by Helen Cooper on behalf of Karen on behalf of Sal on August 26th, 2014 Roxanna to contact for further follow up – Done September 25, 2014 | September 23, 2014 January 20, 2015 |
| DSO Evaluation Forms | Develop a master evaluation form that highlights all feedback from all DSOs Include section in updated marketing package, including Testimonials Could also use for our twitter feeds | Roxanna Andrea |  | April 28th, 2015 |
| REGULARLY REVIEWED |
| Review TOR | Committee | Review every 3 years | Andrea | June 19, 2015 |
| Glossary of Terms | Committee Add an item to the Glossary defining who our clients are. | Review every 3 years Cindy | Andrea | June 19, 2015 |
| Annual Report to OASIS | Committee Chair | Annually in March | Andrea | 2015 |
| Awareness Paper | Committee | Review bi-annually | Andrea | Last completed February 2013. 2015 |
| Ensure OASIS Website has updated Sensory Partners information | Committee | Review annually in January | Joan | 2015 |
| COMPLETED |

Please note: yellow highlighted items are under review given September 24, 2014 meeting